## Sheet1
Employee Time Management System
Sl No | Tasks | Hours
Initial Operations
1 | Design document preparation | 3
2 | Database diagram preparation | 3
3 | Create architecture for front end in angular | 3
4 | Create architecture for service project in asp.net core | 3
Front end estimation(by pages) - Angular
5 | Master page design(Project heading, welcome text,login/logout button) | 2
Authentication:
6 | Login component
| Component design | 1
| Login functionality implementation( validation, authentication, routing etc) | 2
| Unit testing functionality implementation | 0.5
7 | Forgot password component
| Component design | 0.5
| Functionality implementation(validation, api communication etc) | 0.5
| Unit testing functionality implementation | 0.5
8 | Change password component
| Component design | 0.5
| Functionality implementation(validation, api communication etc) | 0.5
| Unit testing functionality implementation | 0.5
Employee
9 | Employee Dashboard
| Component design (Personal & Project info, Edit &Timesheet Link etc) | 3
| Functionality implementation(api communication and databinding, routing etc) | 4
| Unit testing functionality implementation | 0.5
10 | Employee profile edit page
| Component design | 1
| Functionality implementation(databinding,validation,api commn etc) | 3
| Unit testing functionality implementation | 0.5
11 | Employee Timesheet entry component
| Component design | 2
| Functionality implementation(validation, api communication etc) | 2
| Unit testing functionality implementation | 0.5
12 | Employee Timesheet listing component
| Component design( daily view,weekly view, monthly view) | 3
| Functionality implementation(databinding, api commn etc) | 3
| Unit testing functionality implementation | 0.5
Administrator
10 | Administrator Dashboard
| Component design( Employee, project, report link etc) | 1
| Functionality implementation(navigation etc) | 1
| Unit testing functionality implementation | 0.5
11 | Employee list component
| Component design | 2
| Functionality implementation(data fetching and binding etc) | 2
| Unit testing functionality implementation | 0.5
12 | Create/Update employee component
| Component design | 1
| Functionality implementation(validation, api communication etc) | 2
| Unit testing functionality implementation | 0.5
13 | Project list component
| Component design | 1
| Functionality implementation( data fetching and binding) | 2
| Unit testing functionality implementation | 0.5
14 | Create/Update project component
| Component design | 1
| Functionality implementation(validation, api communication etc) | 2
| Unit testing functionality implementation | 0.5
15 | Timesheet entry list page
| Component design (time sheet of all employees(monthly view)) | 3.5
| Functionality implementation(approval, data fetching and binding etc | 4
| Unit testing functionality implementation | 0.5
16 | Report page
| Component design | 2
| Functionality implementation( data fetching and binding) | 2
| Unit testing functionality implementation | 0.5
Backend estimation - ASP.net Core Web API & SQL Server DB
17 | Authentication controller
| Functionality implementation( Login, reset pwd, forgot pwd) | 2
| Unit testing functionality implementation | 0.5
18 | Employee Controller
| Functionality implementation( Employee CRUD operation) | 2
| Unit testing functionality implementation | 0.5
19 | Project Controller
| Functionality implementation( Project CRUD operation) | 2
| Unit testing functionality implementation | 0.5
20 | Timesheet Controller
| Functionality implementation( Timesheet CRUD operation) | 2
| Unit testing functionality implementation | 0.5
21 | Report Controller
| Functionality implementation( Searching and filtering of data) | 2
| Unit testing functionality implementation | 0.5
22 | Authentication and Authorization implementation in API project | 1
23 | SQL Server Database and table creation | 2
Other
24 | Final all feature Integration Testing & Bug fixing | 5
25 | Initial stage - Git hub integration | 2
| Total Hours | 96
| Total Days | 10.5
| Project Completion Date | 2020-07-04
| Project Demo Date | 2020-07-06